## Tx Fdrs Limits-Committed Solns
Transmission and Sub-Transmission Feeder Limitations and Committed Solutions
Committed projects have reached design and construction phase, and applicable information is listed below.
Location:
Maps of Energex’s network showing the location of all Energex’s bulk supply and zone substations are presented via the following link:
https://www.energex.com.au/daprmap2023
References:
The Feeders Forecast and Capacity Tables contains the capacity and forecast loads on the 110 kV, 132 kV and 33 kV feeders for Summer and Winter are available in Appendix F of the following hyperlink:
https://www.energex.com.au/about-us/company-information/company-policies-And-reports/distribution-annual-planning-report
The Substations Forecast and Capacity Table for a summary of planning information for all Bulk Supply, Zone and Joint owned substations are available in Appendix E of the following hyperlink:
https://www.energex.com.au/about-us/company-information/company-policies-And-reports/distribution-annual-planning-report
Energex Distribution Annual Planning Report is prepared and made available solely for information purposes. While care was taken in the preparation of the information in this report, and it is provided in good faith, Energex accepts no responsibility or liability (including without limitation, liability to any person by reason of negligence or negligent mis-statement) for any loss or damage that may be incurred by any person acting in reliance on this information or assumptions drawn from it, except to the extent that liability under any applicable Queensland or Commonwealth of Australia statute cannot be excluded.
It contains assumptions regarding, among other things, economic growth and load forecasts which may or may not prove to be correct. The forecasts included in the document involve subjective judgements and analysis which are subject to significant uncertainties and contingencies, many of which are out of the control of Energex. Energex makes no representation or warranty as to the accuracy, reliability, completeness or suitability for any particular purpose of the information in this document. All information should be independently investigated, reviewed, analysed and verified, and must not be relied upon in connection with any investment proposal or decision.
All financials presented in this document are correct at the time of writing and represent the existing organisational accounting treatment, which may be subject to change. Energy Queensland is still finalising the alignment of its Cost Allocation Methodology between Ergon and Energex, potentially impacting the treatment of some Capital and Operational Project costs.
Limitation | Impact of limitation on the capacity at trans-dist connection point | Committed solution to address the limitation and alternative options considered
T16 - MLY Replace 33kV OH F344 | Nambour BS - No impact | T16 Nambour - MLY Maleny - Re-conductor 33kV Feeder F344 - Estimated cost: $4.4M ±30% - Estimated commissioning date: March 2024 - No alternative options available
KCY – WFD - Establish New 33kV OH Feeder | Beerwah BS - No impact | KCY Kilcoy - WFD Woodford – Construction of a new 33kV feeder to replace aged feeder F447 - Estimated cost: $23.3 ±30% - Estimated commissioning date: June 2024 - Alternative options considered: - Reconductor F447 and F324 - Construct a new double circuit 33kV feeder between SSWFD and SSKCY and recover F447 and F324 - Reconductor F447 and F324 and run 3MVA on-site permanent generator at SSKCY
BWH-MLY-WFD Replace 33kV OH F477 | Beerwah BS - No impact | BWH Beerwah - MLY Maleny - WFD Woodford – Reconductor aged 33kV feeder F477 section (SSMLY-tee to SSWFD) - Estimated cost: $2.6M ±30% - Estimated commissioning date: October 2025 - No alternative options available
AMR-IBL-MRR Replace 33kV OH F339-2 | Gympie BS - No impact | AMR Amamoor - IBL Imbil - MRR Mary River Replace 33kV OH F339-2 and Install Fibre - Estimated cost: $4.8M ±30% - Estimated commissioning date: December 2025 - No alternative options available
T29 Postman’s Ridge -HDN Helidon -Replace 33kV OH F376 | Postman’s Ridge BS - No impact | HDN Helidon – T29 Postman’s Ridge – Reconductor aged 33kV feeder F376 - Estimated cost: $1.9M ±30% - Estimated commissioning date: December 2024 - No alternative options available
CRB-KRA Replace 33kV OH F393 | Burleigh Heads BS - No impact | CBR Currumbin - KRA Kirra Replace 33kV Overhead Feeder 393 - Estimated cost: $2.44M ±30% - Estimated commissioning date: January 2025 - No alternative options available
ESK-TGW Replace 33kV OH F3840 | Lockrose BS - No impact | ESK Esk - TGW Toogoolawah – Reconductor aged 33kV feeder F3840 - Estimated cost: $4.86M ±30% - Estimated commissioning date: December 2026 - No alternative options available
MRB-PGY Replace 33kV OH F3829 | Lockrose BS - No impact | MRB-PGY Replace 33kV OH F3829 - Estimated cost: $1.16M ±30% - Estimated commissioning date: June 2026 - No alternative options available