## Distribution Feeders Committed
Limitation and timing | Location | Committed Solution
BGY - 11kV feeder BGY6A & BGY15A Exceeding capacity TMU | BGY - Burpengary | BGY - Establish a new 11kV feeder - Target Commissioning May 2024 - Cost: $2.51 M ± 30%
BPN - 11kV feeder BPN3 Exceeding capacity TMU | BPN - Browns Plains | BPN - Establish 11kV feeder ties - Target Commissioning Nov 2023 - Cost: $0.87 M ± 30%
CLD - 11kV feeders CLD11, CLD18A & CLD29A Exceeding capacity TMU | CLD - Caloundra | CLD - Establish two new 11kV feeders - Target Commissioning Sep 2024 - Cost: $3.50 M ± 30%
CPL - 11kV feeder CPL2A Exceeding reliability MSS | CPL - Coopers Plains | CPL - Improve reliability on CPL2A - Target Commissioning Dec 2023 - Cost: $0.25 M ± 30%
CRM - 11kV feeder CRM3A Exceeding capacity TMU | CRM - Crestmead | CRM - Establish an 11kV feeder tie - Target Commissioning Aug 2024 - Cost: $0.40 M ± 30%
CRM - 11kV feeder CRM13A Exceeding reliability MSS | CRM - Crestmead | CRM - Improve reliability on CRM13A - Target Commissioning Nov 2023 - Cost: $0.31 M ± 30%
FIS - 11kV feeder FIS7A Exceeding capacity TMU | FIS - Fisherman Island | FIS - Establish a new 11kV feeder - Target Commissioning Nov 2023 - Cost: $0.86 M ± 30%
GYM - 11kV feeder GYM2A Exceeding capacity TMU | GYM - Gympie | GYM - Reconductor GYM2A Mainline - Target Commissioning July 2024 - Cost: $0.46 M ± 30%
MHL - 11kV feeders MHL2A Exceeding capacity TMU | MHL - Mango Hill | MHL - Establish a new 11kV feeder - Target Commissioning Feb 2025 - Cost: $1.00 M ± 30%
MLB - 11kV feeders MLB13A Exceeding capacity TMU | MLB - Mooloolaba | MLB - Establish a new 11kV feeder - Target Commissioning Nov 2024 - Cost: $1.00 M ± 30%
NMC - 11kV feeder NMC15A Exceeding reliability MSS | NMC - North Maclean | NMC - Improve reliabilty on NMC15A - Target Commissioning Nov 2023 - Cost: $0.46 M ± 30%
PPE & CMA - 11kV feeders PPE1B, CMA11A & CMA17A Exceeding capacity TMU | PPE - Pimpama East | PPE - Estabish a new 11kV feeder - Target Commissioning Oct 2024 - Cost: $2.00 M ± 30%
PWC - 11kV feeder PWC4 Exceeding capacity TMU & exceeding reliability MSS | PWC - Palmwoods Central | PWC - Capacity & reliability improvement on PWC4 - Target Commissioning Jul 2024 - Cost: $0.46 M ± 30%
RWD - 11kV feeder RWD1 Exceeding reliability MSS | RWD - Rosewood | RWD - Improve reliabilty on RWD1 - Target Commissioning Nov 2023 - Cost: $0.37 M ± 30%
CBT - 11kV feeder CBT12A Exceeding capacity TMU | CBT - Caboolture | CBT - Establish a new 11kV feeder - Target Commissioning Oct 2024 - Cost: $1.87 M ± 30%
CBT - 11kV feeder CBT8A Exceeding capacity TMU | CBT - Caboolture | CBT - Establish a new 11kV feeder - Target Commissioning Oct 2024 - Cost: $1.87 M ± 30%
CLD - 11kV feeder CLD1A Exceeding capacity TMU | CLD - Caloundra | CLD - Establish a new 11kV feeder - Target Commissioning Sep 2024 - Cost: $3.45 M ± 30%
KLG - 11kV feeder KLG10A Exceeding capacity TMU | KLG - Kallangur | KLG- Establish a new 11kV feeder - Target Commissioning June 2025 - Cost: $0.83 M ± 30%
MHL - 11kV feeder MHL13A Exceeding capacity TMU | MHL - Mango Hill | MHL- Establish a new 11kV feeder - Target Commissioning June 2025 - Cost: $0.47 M ± 30%
CLM- 11kV feeder CLM10 Exceeding capacity TMU | CLM - Coolum | CLM - Establish a new 11kV feeder - Target Commissioning Dec 2024 - Cost: $2.65 M ± 30%
CMD- 11kV feeder CMD11A Exceeding capacity TMU | CMD - Currimundi | CMD - Establish a new 11kV feeder - Target Commissioning June 2025 - Cost: $1.42 M ± 30%
EMP - 11kV feeder EMPGDR21 Exceeding capacity TMU | EMP - Eight Mile Plains | EMP - Establish a new 11kV feeder - Target Commissioning Aug 2025 - Cost: $1.77 M ± 30%
HTL - 11kV feeder HTL6A Exceeding capacity TMU | HTL - Hamilton Lands | HTL - Improve reliabilty on HTL6A - Target Commissioning June 2025 - Cost: $0.23 M ± 30%
HWD - 11kV feeder HWD5A Exceeding capacity TMU | HWD - Heathwood | HWD - Establish a new 11kV feeder - Target Commissioning Aug 2025 - Cost: $0.92 M ± 30%
AGT - 11kV feeder AGT31A Exceeding capacity TMU | AGT - Algester | AGT - Establish a new 11kV feeder - Target Commissioning Aug 2025 - Cost: $0.92 M ± 30%
JBB - 11kV feeder JBB1B Exceeding capacity TMU | JBB - Jimboomba | JBB - Establish a new 11kV feeder - Target Commissioning Aug 2025 - Cost: $2.75 M ± 30%
JBB - 11kV feeder JBB4A Exceeding capacity TMU | JBB - Jimboomba | JBB - Establish a new 11kV feeder - Target Commissioning Aug 2025 - Cost: $2.75 M ± 30%
KLG - 11kV feeder KLG2A Exceeding capacity TMU | KLG- Kallangur | KLG - Establish a new 11kV feeder - Target Commissioning June 2025 - Cost: $0.83 M ± 30%
MFN - 11kV feeder MFN13A Exceeding capacity TMU | MFN- Morayfield North | MFN - Establish a new 11kV feeder - Target Commissioning June 2025 - Cost: $0.95 M ± 30%
MHL - 11kV feeder MHL25A Exceeding capacity TMU | MHL- Mango Hill | MHL - Establish a new 11kV feeder - Target Commissioning June 2025 - Cost: $0.47 M ± 30%
MLB - 11kV feeder MLB2A Exceeding capacity TMU | MLB- Mooloolaba | MLB - Establish a new 11kV feeder - Target Commissioning Nov 2024 - Cost: $0.66 M ± 30%
NMC - 11kV feeder NMC2A Exceeding capacity TMU | NMC- North Maclean | NMC - Establish a new 11kV feeder - Target Commissioning Aug 2025 - Cost: $1.34 M ± 30%
PWC - 11kV feeder PWC3 Exceeding capacity TMU | PWC- Palmwoods Central | PWC - Improve reliabilty on PWC3 - Target Commissioning Sep 2024 - Cost: $0.80 M ± 30%
PWC - 11kV feeder PWC6 Exceeding capacity TMU | PWC- Palmwoods Central | PWC - Improve reliabilty on PWC6 - Target Commissioning Aug 2024 - Cost: $0.60 M ± 30%
WSE - 11kV feeder WSE3A Exceeding capacity TMU | WSE- Whiteside | WSE - Improve reliabilty on WSE3A - Target Commissioning Sep 2024 - Cost: $0.42 M ± 30%