## Subs Limits & Committed Solns
Substation Limitations and Committed Solutions
Committed projects have reached design and construction phase, and applicable information is listed below.
Location:
Maps of Energex’s network showing the location of all Energex’s bulk supply and zone substations are presented via the following link:
https://www.energex.com.au/daprmap2023
References:
The Substations Forecast and Capacity Table for a summary of planning information for all Bulk Supply, Zone and Joint owned substations are available in Appendix E of the following hyperlink:
https://www.energex.com.au/about-us/company-information/company-policies-And-reports/distribution-annual-planning-report
Energex Distribution Annual Planning Report is prepared and made available solely for information purposes. While care was taken in the preparation of the information in this report, and it is provided in good faith, Energex accepts no responsibility or liability (including without limitation, liability to any person by reason of negligence or negligent mis-statement) for any loss or damage that may be incurred by any person acting in reliance on this information or assumptions drawn from it, except to the extent that liability under any applicable Queensland or Commonwealth of Australia statute cannot be excluded.
It contains assumptions regarding, among other things, economic growth and load forecasts which may or may not prove to be correct. The forecasts included in the document involve subjective judgements and analysis which are subject to significant uncertainties and contingencies, many of which are out of the control of Energex. Energex makes no representation or warranty as to the accuracy, reliability, completeness or suitability for any particular purpose of the information in this document. All information should be independently investigated, reviewed, analysed and verified, and must not be relied upon in connection with any investment proposal or decision.
All financials presented in this document are correct at the time of writing and represent the existing organisational accounting treatment, which may be subject to change. Energy Queensland is still finalising the alignment of its Cost Allocation Methodology between Ergon and Energex, potentially impacting the treatment of some Capital and Operational Project costs.
Limitation | Impact of limitation on the capacity at trans-dist connection point | Committed solution to address the limitation and alternative options considered
ABM Abermain - Powerlink Secondary System Replacement | Abermain BS - No impact | ABM Abermain - Powerlink Secondary System Replacement - Estimated cost: $1.5M±30% - Estimated commissioning September 2023 - No alternative options available | ABM Abermain - Powerlink Secondary System Replacement | ABM Abermain - Powerlink Secondary System Replacement
PBH Palm Beach - Replace 33/11kV Transformers | Burleigh Heads BS - No impact | PBH Palm Beach Replace 33/11kV Transformers - Estimated cost: $7.1M ±30% - Estimated commissioning date: April 2024 - Alternative options considered: - Replace the existing transformers with 1 x 25MVA transformer and convert the existing 33kV feeder F396 to 11kV to provide a backup supply | PBH Palm Beach Replace 33/11kV Transformers | PBH Palm Beach Replace 33/11kV Transformers
MCE Establish Mount Crosby East Zone Substation | Abermain BS - No impact | MCE Establish Mount Crosby East Zone Substation - Estimated cost: $20.0M ±30% - Estimated commissioning date: July 2025 - No alternative options available | MCE Establish Mount Crosby East Zone Substation | MCE Establish Mount Crosby East Zone Substation
SHW Sherwood - Improve Backup Protection Reach | Tennyson BS - No impact | SHW Sherwood - Improve 11kV Backup Protection Reach & Replace Ageing Relays - Estimated cost: $2.6M ±30% - Estimated commissioning date: November 2023 - No alternative options available | QPT Queensport - Improve 11kV Backup Protection Reach | QPT Queensport - Improve 11kV Backup Protection Reach
ALY Annerley - Improve 11kV Backup Protection Reach | Tennyson BS - No impact | ALY Annerley - Improve 11kV Backup Protection Reach - Estimated cost: $1.3M ±30% - Estimated commissioning date: March 2024 - No alternative options available
WGC Wintergarden Complex - Improve Transformer Low Voltage Backup Protection | Charlotte Street BS - No impact | WGC Wintergarden Complex - Improve Transformer Backup Protection - Estimated cost: $0.5M ±30% - Estimated commissioning date: July 2024 - Alternative options considered: Install OC+EF relay for transformer backup protection
NME National Mutual Insurance - Improve Transformer Low Voltage Backup Protection | Charlotte Street BS - No impact | NME National Mutual Insurance - Improve Transformer Backup Protection - Estimated cost: $0.5M ±30% - Estimated commissioning date: June 2024 - Alternative options considered: Install OC+EF relay for transformer backup protection
AMR Amamoor– Replace 11kV Outdoor Isolators | Gympie BS - No impact | AMR Amamoor– Replace 11kV Outdoor Isolators - Estimated cost: $1,566,098 ±30% - Estimated commissioning date: March 2024 - No alternative options available
RIS - Replace Protection Relay | Loganlea BS -No impact | RIS Russell Island - Replace Protection Relay - Estimated cost: $979,082 ±30% - Estimated commissioning: October 2024 - No alternative options available
FDS Flinders Replace 11kV & 33kV outdoor isolators | Raceview BS - No impact | FDS Flinders Zone Substation – Replace 33kV and 11kV outdoor isolators - Estimated cost: $1,470,760 ±30% - Estimated commissioning: April 2024 - No alternative options available
QEE MacArthur Central Plaza – Replace Protection Relays & Establish Transformer Backup Protection | Charlotte St BS -No impact | QEE MacArthur Central Plaza – Replace Protection Relays & Establish Transformer Backup Protection - Estimated cost: $627,602 ±30% - Estimated commissioning: April 2024 - No alternative options available
NGE Nudgee - Replace 11kV switchgear | Nudgee BS - No impact | NGE Nudgee - Replace 11kV Switchgear - Estimated cost: $10,554,528 ±30% - Estimated commissioning date: September 2024 - No alternative options available
BDS Beaudesert - Replace Protection Relay | Beaudesert BS -No impact | BDS Beaudesert - Replace Protection Relays - Estimated cost: $2,031,064 ±30% - Estimated commissioning: May 2024 - No alternative options available
SIS Stradbroke Island Replace 33/11kV TR3, 33kV Bus and CB3T32 | Beenleigh BS - No impact | SIS Stradbroke Island - Replace 33/11kV TR3, CB3T32 and 33kV bus - Estimated cost: $7,926,252 ±30% - Estimated commissioning: November 2024 - No alternative options available
DBS - Doboy Bulk Supply Improve 11kV Backup Protection Reach | Doboy BS -No impact | SSDBS - Doboy Bulk Supply Improve 11kV Backup Protection Reach - Estimated cost: $909,989 ±30% - Estimated commissioning: September 2024 - No alternative options available
CST Charlotte Street - SACS Upgrade & replace DUOBIAS | Murarrie BS -No impact | CST Charlotte Street – Upgrade 110kV Feeder Protection and Replace Duobias Relays - Estimated cost: $2,739,450 ±30% - Estimated commissioning: December 2024 - No alternative options available
SPD Surfers Paradise – Improve Back-up Protection Reach & Replace Obsolete Relays | Merrimac BS & Molendinar BS -No impact | SPD Surfers Paradise - Improve Back-up Protection Reach & Replace Obsolete Relays - Estimated cost: $2,903,189 ±30% - Estimated commissioning: April 2025 - No alternative options available
NGE Nudgee- Replace 4 x 110kV CBs | Nudgee BS -No impact | NGE Nudgee - Replace 145kV circuit breakers, 145kV current transformers, 33kV voltage transformer, obsolete protection relays - Estimated cost: $3,209,477 ±30% - Estimated commissioning: February 2025 - No alternative options available
ACR Albany Creek - Replace 6 x 11kV CB's & 2 x 11kV Relays | Brendale BS -No impact | ACR Albany Creek - Replace problematic 12kV circuit breakers, obsolete protection schemes, obsolete protection relays - Estimated cost: $1,658,445 ±30% - Estimated commissioning: February 2024 - No alternative options available
LGL - Improve 11kV Backup Protection | Loganlea BS -No impact | LGL Loganlea - Improve 11kV Backup Protection & Replace Obsolete Relays - Estimated cost: $1,040,999 ±30% - Estimated commissioning: December 2023 - No alternative options available
MRB Recover 33kV and 11kV Outdoor Isolators | Lockrose BS - No impact | MRB Murrumba Zone Substation – Recover 33kV and 11kV outdoor isolators - Estimated cost: $3,744,124 ±30% - Estimated commissioning: March 2024 - No alternative options available
GLY - Improve 11kV Backup Protection | Stafford BS / Brendale BS -No impact | GLY Grovely - Improve 11kV Backup Protection - Estimated cost: $2,988,165 ±30% - Estimated commissioning: January 2024 - No alternative options available
SPF - Improve 11kV Backup Protection and Replace Obsolete Relays | Goodna BS - No impact | SPF Springfield & STC Springfield Town Centre - Improve 11kV Backup Protection & Replace Obsolete Relays - Estimated cost: $1,598,809 ±30% - Estimated commissioning: Jun 2024 - No alternative options available
CRB - Improve 11kV Backup Protection | Burleigh Heads BS - No impact | CRB Currumbin - Improve 11kV Backup Protection - Estimated cost: $1,069,564 ±30% - Estimated commissioning: January 2024 - No alternative options available
SPO – Improve Back-up Protection Reach & Upgrade Protection Scheme | Merrimac BS & Molendinar BS -No impact | SPO South Port - Improve Back-up Protection Reach & Upgrade Protection Scheme - Estimated cost: $2.5m ±30% - Estimated commissioning: August 2024 - No alternative options available
BDA – Improve Back-up Protection Reach & Upgrade Protection Scheme | Tennyson BS - No impact | BDA Burranda - Improve Back-up Protection Reach & Upgrade Protection Scheme - Estimated cost: $951,576m ±30% - Estimated commissioning: June 2024 - No alternative options available
CNB - Improve Backup Protection Reach and Upgrade TR DIFF Scheme | Beenleigh BS - No impact | CNB Connubia - Improve Backup Protection Reach and Upgrade TR DIFF Scheme - Estimated cost: $1,499,167 ±30% - Estimated commissioning: May 2024 - No alternative options available
CPS - Improve 11kV Backup Protection Reach | Cleveland BS -No impact | CPS Capalaba South - Improve 11kV Backup Protection Reach - Estimated cost: $940,113 ±30% - Estimated commissioning: June 2024 - No alternative options available
TWG - Replace 33kV OD isolators | T30 Ashgrove West BS - No impact | TWG Toowong - Replace 33kV OD isolators - Estimated cost: $1,414,424 ±30% - Estimated commissioning: December 2024 - No alternative options available
YDA - Yandina Replace KBCH and Duobias Relays | Nambour BS -No impact | YDA Yandina - Upgrade TR DIFF Scheme and Replace Protection Relays - Estimated cost: $1,371,445 ±30% - Estimated commissioning: January 2024 - No alternative options available
GNA - Replace DUOBIAS/Argus 1 Relays | H38 Goodna BS -No impact | GNA Goodna - Replace DUOBIAS/Argus 1 Relays - Estimated cost: $1,786,563 ±30% - Estimated commissioning: December 2024 - No alternative options available
CCY Upgrade AFLC unit | Cades County BS - No impact | CCY Cades County – Replace Station Services Transformers, Replace Problematic Relays & Rectify Capacitor Banks - Estimated cost: $1,647,798 ±30% - Estimated commissioning: May 2024 - No alternative options available
NSD - Replace Argus 1 Relays | Murarrie BS - No impact | NSD Newstead & SSCGT- Replace Protection Relays - Estimated cost: $1,543,629 ±30% - Estimated commissioning: September 2024
ENG Improve 11kV Backup Protection Reach | Stafford BS - No impact | ENG Eneggora - Improve 11kV Backup Protection Reach - Estimated cost: $1,017,203 ±30% - Estimated commissioning: July 2024
ABY - Replace KBCH120 on TR1 & SACS Upgrade | Abermain BS - No impact | ABY Amberley – Replace KBCH120 on TR1 and Improve Backup Protection Reach - Estimated cost: $1,229,938 ±30% - Estimated commissioning: August 2024 - No alternative options available
YMT - Replace KBCH and DUOBIAS Relays | Raceview BS - No impact | YMT Yamanto – Replace Problematic Relays and Improve 11kV Backup Protection - Estimated cost: $1,559,585 ±30% - Estimated commissioning: June 2025 - No alternative options available
MHL - Improve 11kV Backup Reach & Replace IS3T19 | GFN Griffin BS / HIL Hayes Inlet BS - No impact | MHL Mango Hill - Improve 11kV Backup Reach & Repalce IS3T19 - Estimated cost: $1,744,924 ±30% - Estimated commissioning: September 2024 - No alternative options available
STT - Improve 11kV BackUp Protection | T108 Beenleigh BS - No impact | STT Stapylton - Improve 11kV Backup Prot - Estimated cost: $1,002,589 ±30% - Estimated commissioning: May 2024 - No alternative options available
YTA Yatala - Replace Motorised Isolator IS3T29 | T108 Beenleigh BS - No impact | YTA Yatala - Replace motorised isolator IS3T29 - Estimated cost: $1,051,706 ±30% - Estimated commissioning: April 2024 - No alternative options available
RLA Rocklea - Improve 11kV Backup Reach and Replace Relays | Archerfield BS - No impact | RLA Rocklea - Improve 11kV backup protection reach and replace protection relays - Estimated cost: $492,542 ±30% - Estimated commissioning: July 2024 - No alternative options available
CHL Camp Hill - Improve 11kV Backup Protection | Coorparoo BS - No impact | CHL Camp Hill - Improve 11kV Backup Protection - Estimated cost: $1,154,963 ±30% - Estimated commissioning: October 2024 - No alternative options available
MLS Mclachlan Street - Replace Problematic Relays & SACS Upgrade | T30 Ashgrove West BS - No impact | MLS Mclachlan Street - Replace problematic relays & SACS upgrade - Estimated cost: $666,063 ±30% - Estimated commissioning: October 2024 - No alternative options available
IPL Innisplain - Improve 11kV Backup Protection | Beaudesert BS - No impact | IPL Innisplain - Improve 11kV Backup Protection - Estimated cost: $51,639 ±30% - Estimated commissioning: June 2024 - No alternative options available
IPS Ipswich South - Improve 11kV Backup Protection Reach | Raceview BS - No impact | IPS Ipswich South – Improve 11kV Backup Protection Reach & Replace Argus 1 Relays - Estimated cost: $1,301,675 ±30% - Estimated commissioning: August 2024 - No alternative options available
BRT Brighton - Improve 11kV backup protection reach | Sandgate BS - No impact | BRT Brighton - Improve 11kV backup protection reach - Estimated cost: $1,032,506 ±30% - Estimated commissioning: January 2025 - No alternative options available
BIS Bribie Island - Improve 11kV Backup Protection Reach | Caboolture BS - No impact | BIS Bribe Island - Improve 11kV Backup Protection Reach - Estimated cost: $957,933 ±30% - Estimated commissioning: July 2024 - No alternative options available
DBY Deception Bay Install POPS Scheme | Hays Inlet BS - No impact | SSDBY Deception Bay - Install POPS Scheme - Estimated cost: $117,536 ±30% - Estimated commissioning: March 2024 - No alternative options available
KRN Kedron - Replace 33kV OD Isolators | Stafford BS - No impact | KRN Kedron - Replace 33kV OD isolators - Estimated cost: $1,640,123 ±30% - Estimated commissioning: September 2026 - No alternative options available
RWD Rosewood - Rebuild Substation to Replace Ageing Assets | Abermain BS - No impact | RWD Rosewood - Rebuild Substation to Replace Ageing Assets - Estimated cost: $10,926,900 ±30% - Estimated commissioning: June 2026 - No alternative options available
WED West End – Replace 11kV Switchgear | Rocklea BS - No impact | WED West End – Replace 11kV Switchgear - Estimated cost: $5,768,404 ±30% - Estimated commissioning: February 2026 - No alternative options available
ESK - Impr 11kV Backup Prot Reach | Lockrose BS - No impact | ESK Esk - Impr 11kV Backup Prot Reach - Estimated cost: $1,452,433 ±30% - Estimated commissioning: November 2024 - No alternative options available
UMG Upper Mt Gravatt - Replace motorised isolator IS3T19 | Belmont BS - No impact | UMG Upper Mt Gravatt - Replace motorised isolator IS3T19 - Estimated cost: $1,366,343 ±30% - Estimated commissioning: February 2025 - No alternative options available
HPK Holland Park - Replace 33/11kV Transformer TR2 | Coorparoo BS - No impact | HPK Holland Park - Replace 33/11kV Transformer TR2 - Estimated cost: $5,245,528 ±30% - Estimated commissioning: February 2025 - No alternative options available
THL - Improve 11kV Backup Protection | Gatton BS - No impact | THL - Improve 11kV Backup Protection - Estimated cost: $258,683 ±30% - Estimated commissioning: March 2025 - No alternative options available
PGY - Replace DUOBIAS Relay on RG1 | Lockrose BS - No impact | PGY - Replace DUOBIAS Relay on RG1 - Estimated cost: $269,401 ±30% - Estimated commissioning: January 2025 - No alternative options available
MCW - Imprrove 11kV Backup Protection | Abermain BS - No impact | MCW Mt Crosby West Bank - Improve Backup Protection Reack - Estimated cost: $411,210 ±30% - Estimated commissioning: August 2024 - No alternative options available
CBW - Replace 33kV VT38 & VT39 | Caboolture BS - No impact | CBW - Replace 33kV VT38 & VT39 - Estimated cost: $483,388 ±30% - Estimated commissioning: January 2025 - No alternative options available
CPR - Imp 11kV back prot reach | Coorparoo BS - No impact | CPR Coorparoo - Improve Backup Protection Reack - Estimated cost: $508,032 ±30% - Estimated commissioning: August 2025 - No alternative options available
HTN - Improve Backup Protection Reach | Nudgee BS - No impact | HTN Hamilton - Improve Backup Protection Reack - Estimated cost: $712,873 ±30% - Estimated commissioning: September 2025 - No alternative options available
T70 - Repalce KBCH and Argus 1 Relays | Sunrise Hills BS - No impact | T70 - Repalce KBCH and Argus 1 Relays - Estimated cost: $775,551 ±30% - Estimated commissioning: May 2025 - No alternative options available
BLN Beenleigh North-Improve 11kV Backup Protection Reach | Beenleigh BS - No impact | BLN Beenleigh North-Improve 11kV Backup Protection Reach - Estimated cost: $979,556 ±30% - Estimated commissioning: February 2025 - No alternative options available
JBB - Disconnect Capacitor Bank & 11kV Feeder Cutover | Jimboomba BS - No impact | JBB - Disconnect Capacitor Bank & 11kV Feeder Cutover - Estimated cost: $1,123,035 ±30% - Estimated commissioning: February 2025 - No alternative options available
SSSPC - Replace DUOBIAS on TR1 | Gatton BS - No impact | SPC Spring Creek - Repalce DUOBIAS on TR1 - Estimated Cost: $1,403,395 ±30% - Estimated commissioning: September 2025 - No alternative options available
CVL - Improve 11kV Backup Protection | Cleveland BS - No impact | CVL - Improve 11kV Backup Protection - Estimated cost: $1,652,926 ±30% - Estimated commissioning: April 2025 - No alternative options available
MGL - Improve 11kV Backup Protection Reach | Abermain BS - No impact | MGL - Improve 11kV Backup Protection Reach - Estimated cost: $2,817,994 ±30% - Estimated commissioning: March 2026 - No alternative options available
BHD - SRTS SE GC SSBHD Building Remediation Works | Burleigh Heads BS - No impact | BDH - SRTS SE GC SSBHD Building Remediation Works - Estimated cost: $2,895,103 ±30% - Estimated commissioning: August 2024 - No alternative options available
T78 Install New 15kVA 33/11kV Transformer & Replace 33kV CBs | Lockrose BS - No impact | T78 Install New 15kVA 33/11kV Transformer & Replace 33kV CBs - Estimated cost: $4,760,796 ±30% - Estimated commissioning: July 2026 - No alternative options available
CMY - Replace TR1 With 33/11kV 5/8MVA Transformer | Lockrose BS - No impact | CMY Coominya - Replace 33/11kV TR1, CB3T12 and Recloser Controllers - Estimated cost: $4,877,333 ±30% - Estimated commissioning: June 2027 - No alternative options available
TGW - Replace 33kV Outdoor Isolators | Ashgrove West BS - No impact | TGW Toogoolawah - Replace 33kV OD isolators - Estimated cost: $9,417,589 ±30% - Estimated commissioning: May 2027 - No alternative options available
LDM - Replace 8x33kV Circuit Breakers | Lytton Bulk Supply BS - No impact | LDM - Replace 8x33kV Circuit Breakers - Estimated cost: $13,511,305 ±30% - Estimated commissioning: March 2027 - No alternative options available
PTE Petrie - Establish 33/11kV Zone Substation | Griffin BS - No impact | PTE Petrie - Establish 33/11kV Zone Substation - Estimated cost: $22.7M ±30% - Estimated commissioning date: July 2026 - Alternative option considered: - Replace ageing transformers at SSKLG, establish new 11kV feeders to supply the new development areas and establish a new 33/11kV zone substation at Petrie | HMT Hemmant - Replace 33/11kV Transformer TR2 | HMT Hemmant - Replace 33/11kV Transformer TR2
TRP Tarampa – Replace TR1, CB3T12, isolators & BSM | Lockrose BS - No impact | TRP Tarampa - Rebuild Substation to Replace Ageing Assets - Estimated cost: $12,104,643 ±30% - Estimated commissioning: April 2027 - No alternative options available
BHL Bald Hills - Replace obsolete relays and improve backup protection reach | Sandgate BS - No impact Brendale BS - No impact | BHL Bald Hills - Replace Replace Obsolete Relays and Improve 11kV BU Reach - Estimated cost: $1,562,933 ±30% - Estimated commissioning: March 2026 - No alternative options available
PRG - Postmans Ridge - Imp 11kV Backup Prot Reach | Postmans Ridge BS - No impact | PRG (T29) Postmans Ridge - Improve 11kV Backup Protection & Replace End of Life / Problematic Relays - Estimated cost: $901,269 ±30% - Estimated commissioning: June 2025 - No alternative options available
BCR Bells Creek Central - Establish 132/11kV Zone Substation | Palmwoods BS - No impact | BCR Bells Creek Central - Establish 132/11kV Zone Substation - Estimated cost: $109,754,831 ±30% - Includes 132/11kV zone substation, 132kV double circuit OH/UG feeders, 4 x 11kV feeders - Estimated commissioning date: February 2027 - Alternative options considered: - Install 2 x 11kV feeders from SSCLD - Establish Meridan Plains 132/33kV Bulk Supply + SSBCR 33/11kV Zone Substation - Establish Bells Creek North 132/33kV Bulk Supply + SSBCR 33/11kV Zone Substation - Establish Bells Creek North 132/33kV Bulk Supply + 4 x 11kV feeders to supply Aura load - Contract with proponent for 24MW/39.75MWh BESS NOTE: Approved by the Board to be submitted to the shareholding Ministers. Pending approval by the shareholding Ministers at the time of 2023 DAPR publication. | PBH Palm Beach Replace 33/11kV Transformers | PBH Palm Beach Replace 33/11kV Transformers